## Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Definition |  | 20 | 22 | -2 | 1 |  |  |  | 110%
1.1 | Initial Discussion for Ideas | Everyone | 4 | 6 | -2 | 1 | 2023-11-28 | 2023-11-29 | 2 | 150% | bar: WEEK 1 T to WEEK 1 W; WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
1,2 | Research of Information | Everyone | 4 | 3 | 1 | 1 | 2023-12-02 | 2023-12-02 | 1 | 75% | bar: WEEK 1 W; WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
1,3 | Project Planning | Everyone | 8 | 9 | -1 | 1 | 2023-12-04 | 2023-12-06 | 3 | 112.5% | bar: WEEK 1 R to WEEK 1 F; WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
1,4 | Architecture Modeling | Everyone | 2 | 2 | 0 | 1 | 2023-12-11 | 2023-12-11 | 1 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
1.5 | Sent Project Proposal | Everyone | 2 | 2 | 0 | 1 | 2023-12-12 | 2023-12-12 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
2 | Project Setup |  | 16 | 18 | -2 | 2 |  |  |  | 112.5%
2.1 | User Stories | Everyone | 4 | 4 | 0 | 2 | 2023-12-15 | 2023-12-15 | 1 | 100% | bar: WEEK 3 M to WEEK 3 T; WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
2.2 | Balsamiq Wireframes | Everyone | 6 | 6 | 0 | 2 | 2023-12-16 | 2023-12-17 | 2 | 100% | bar: WEEK 3 W to WEEK 4 M; WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
2.3 | Function Points & COCOMO Estimation | Everyone | 4 | 6 | -2 | 2 | 2023-12-18 | 2023-12-19 | 2 | 150% | bar: WEEK 4 M to WEEK 4 T; WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
2,4 | Documentation | Everyone | 2 | 2 | 0 | 2 | 2023-12-20 | 2023-12-20 | 1 | 100% | bar: WEEK 4 W to WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
3 | Back-end/Front-end 1 |  | 75 | 86 | -11 | 3 |  |  |  | 114.7%
3.1 | Inizialition of the project setup | Everyone | 3 | 5 | -2 | 3 | 2023-12-21 | 2023-12-21 | 1 | 166.7% | bar: WEEK 5 M to WEEK 5 R; WEEK 8 M
3,2 | MySQL download and setup, user management | Ambrogio, Fè | 3 | 3 | 0 | 3 | 2023-12-22 | 2023-12-22 | 1 | 100% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
3,3 | Front-end home page,navbar and login | Buccigrossi | 8 | 7 | 1 | 3 | 2023-12-26 | 2023-12-27 | 2 | 87.5% | bar: WEEK 5 M to WEEK 5 R; WEEK 8 M
3,4 | Back-end fetching with front-end | Ambrogio, Fè | 4 | 6 | -2 | 3 | 2023-12-26 | 2023-12-27 | 2 | 150% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 F; WEEK 8 M
3,5 | Registration page front-end | Buccigrossi | 6 | 4 | 2 | 3 | 2023-12-29 | 2023-12-29 | 1 | 66.67% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
3,6 | Registration back-end | Ambrogio, Fè | 6 | 6 | 0 | 3 | 2023-12-30 | 2023-12-30 | 1 | 100% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
3,7 | Home page first version | Ambrogio, Buccigrossi | 6 | 8 | -2 | 3 | 2024-01-02 | 2024-01-04 | 3 | 133.3% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 6 M to WEEK 6 R; WEEK 8 M
3,8 | DB auction and items | Fè | 2 | 2 | 0 | 3 | 2024-01-02 | 2024-01-02 | 1 | 100% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 6 M; WEEK 8 M
3,9 | Settings page front-end | Buccigrossi | 8 | 9 | 0 | 3 | 2024-01-05 | 2024-01-07 | 3 | 112.5% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 6 M to WEEK 6 R; WEEK 8 M
3,10 | Settings back-end | Buccigrossi, Fè | 10 | 14 | -4 | 3 | 2024-01-05 | 2024-01-08 | 4 | 140% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 6 T to WEEK 6 R; WEEK 8 M
3,11 | Back-end auction management, auction page | Ambrogio | 3 | 3 | -1 | 3 | 2024-01-06 | 2024-01-06 | 1 | 100% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 6 F; WEEK 8 M
3,12 | Items management DB and visual in each auction | Ambrogio | 6 | 8 | -2 | 4 | 2024-01-07 | 2024-01-09 | 3 | 133.3% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 6 W to WEEK 7 T; WEEK 8 M
3,13 | Fix back-end auctions managements | Fè | 3 | 4 | -1 | 4 | 2024-01-10 | 2024-01-11 | 2 | 133.3% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 6 W to WEEK 7 T; WEEK 8 M
3,14 | Fix problems settings with DB | Buccigrossi | 3 | 2 | 1 | 4 | 2024-01-10 | 2024-01-11 | 2 | 66.67% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 6 F to WEEK 7 M; WEEK 8 M
3,15 | Search Page and relative back-end | Ambrogio | 4 | 5 | -1 | 4 | 2024-01-10 | 2024-01-11 | 2 | 125% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 7 M; WEEK 8 M
4 | Back-end/Front-end 2 |  | 48 | 61 | -13 | 3 |  |  |  | 127.1%
4,1 | Myoffer page and relative back-end | Ambrogio, Buccigrossi | 4 | 6 | -2 | 4 | 2024-01-13 | 2024-01-14 | 2 | 150% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 7 T to WEEK 7 W; WEEK 8 M
4,2 | DB image management | Fè | 4 | 5 | -1 | 4 | 2024-01-13 | 2024-01-14 | 2 | 125% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 7 W; WEEK 8 M
4,3 | Insert auction page | Buccigrossi | 3 | 3 | 0 | 4 | 2024-01-15 | 2024-01-15 | 1 | 100% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 7 R; WEEK 8 M
4,4 | Home page last version | Ambrogio | 4 | 4 | 0 | 4 | 2024-01-16 | 2024-01-16 | 1 | 100% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 7 F to WEEK 8 M
4,5 | Fix problems back-end/front-end | Everyone | 4 | 8 | -4 | 4 | 2024-01-17 | 2024-01-19 | 3 | 200% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 7 F to WEEK 8 M
4,6 | Api Gateway Filtering and distribute servers | Ambrogio, Fè | 6 | 8 | -2 | 4 | 2024-01-22 | 2024-01-24 | 3 | 133.3% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M to WEEK 8 W
4,7 | RabbitMQ setup, docker image | Buccigrossi | 5 | 5 | 0 | 4 | 2024-01-22 | 2024-01-24 | 3 | 100% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M; WEEK 8 R to WEEK 8 F
4,8 | RabbitMQ manage queue and receivers | Everyone | 8 | 9 | -1 | 4 | 2024-01-26 | 2024-01-28 | 1 | 112.5% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M; WEEK 8 F
4,9 | Fix upload image problem back-end | Everyone | 2 | 6 | -4 | 4 | 2024-01-29 | 2024-01-30 | 2 | 300% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
4,10 | Refine CSS and popup | Amrbogio, Buccigrossi | 4 | 3 | 1 | 4 | 2024-01-31 | 2024-01-31 | 1 | 75% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M
4.11 | Control data insertion registration, settings back-end | Fè | 4 | 4 | 0 | 4 | 2024-01-31 | 2024-01-31 | 1 | 100% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M to WEEK 8 T
5 | Containerization and Frontend Fixes |  | 23 | 35 | -12 | 5 |  |  |  | 152.2%
5,1 | Docker setup and first version of mysql container | Everyone | 4 | 5 | -1 | 5 | 2024-02-02 | 2024-02-03 | 2 | 125% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M; WEEK 9 M to WEEK 9 W
5,2 | Containerization front-end and back-end servers | Everyone | 6 | 8 | -2 | 5 | 2024-02-05 | 2024-02-06 | 2 | 133.3% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M; WEEK 9 T to WEEK 9 R
5,3 | Docker compose first attempt | Everyone | 4 | 6 | -2 | 5 | 2024-02-07 | 2024-02-09 | 3 | 150% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M; WEEK 9 T to WEEK 10 M
5,4 | Fix docker networks problems | Everyone | 4 | 11 | -7 | 5 | 2024-02-09 | 2024-02-12 | 4 | 275% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M; WEEK 10 T to WEEK 10 W
5,5 | Final version deployment | Everyone | 5 | 5 | 0 | 5 | 2024-02-15 | 2024-02-16 | 2 | 100% | bar: WEEK 5 M; WEEK 5 W to WEEK 5 R; WEEK 8 M; WEEK 10 W to WEEK 10 R
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 182 | 222 | -40 | 60 | 3.0333 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 |  | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 182 | 178.9667 | 175.9333 | 172.9 | 169.8667 | 166.8333 | 163.8 | 160.7667 | 157.7333 | 154.7 | 151.6667 | 148.6333 | 145.6 | 142.5667 | 139.5333 | 136.5 | 133.4667 | 130.4333 | 127.4 | 124.3667 | 121.3333 | 118.3 | 115.2667 | 112.2333 | 109.2 | 106.1667 | 103.1333 | 100.1 | 97.0667 | 94.0333 | 91 | 87.9667 | 84.9333 | 81.9 | 78.8667 | 75.8333 | 72.8 | 69.7667 | 66.7333 | 63.7 | 60.6667 | 57.6333 | 54.6 | 51.5667 | 48.5333 | 45.5 | 42.4667 | 39.4333 | 45 | 41 | 37 | 33 | 29 | 25 | 21 | 17 | 13 | 9 | 5 | 1
[10 empty] | ESTIMATE | 182 | 179 | 176 | 173 | 170 | 167 | 164 | 162 | 160 | 156 | 153 | 150 | 147 | 144 | 141 | 136 | 133 | 129 | 126 | 123 | 120 | 116 | 110 | 107 | 104 | 95 | 88 | 80 | 75 | 70 | 65 | 59 | 52 | 48 | 45 | 41 | 39 | 36 | 33 | 30 | 25 | 20 | 17 | 14 | 11 | 8 | 5 | 2 | 47 | 39 | 31 | 23 | 15 | 7 | -1 | -7 | -13 | -19 | -23 | -27 |  | 4658
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 4 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 4 | 3 | 3 | 3 | 4 | 6 | 3 | 3 | 9 | 7 | 8 | 5 | 5 | 5 | 6 | 7 | 4 | 3 | 4 | 2 | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 7 | 3 | 2 | 4 | 4 | 3 | 2 | 4 | 3 | 3 | 2 | 3 | 2 |  | 222
[10 empty] | HRS REMAINING | 179 | 176 | 173 | 170 | 167 | 164 | 162 | 160 | 156 | 153 | 150 | 147 | 144 | 141 | 136 | 133 | 129 | 126 | 123 | 120 | 116 | 110 | 107 | 104 | 95 | 88 | 80 | 75 | 70 | 65 | 59 | 52 | 48 | 45 | 41 | 39 | 36 | 33 | 30 | 25 | 20 | 17 | 14 | 11 | 8 | 5 | 2 | -5 | 39 | 31 | 23 | 15 | 7 | -1 | -7 | -13 | -19 | -23 | -27 | -29 |  | 4395
[23 empty] | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 6
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Product Backlog
Story Name | Story Description | Priority | Status
AUTHENTICATION | As an unregistered user, I want to be able to register to the application so that I can access it. | 1 High | Done
| As a registered non-logged user, I want to perform the login so that I use the services. | 1 High | Done
| As a registered user, I want to perform the logout so I can disconnect safely. | 1 High | Done
PROFILE | As a registered user, I want to access my Profile Page so that I can display my details. | 2 Med | Done
| As a registered user, I want to access my Settings Page so that I can manage my profile. | 2 Med | Done
| As a registered user, I want to prove my credentials so that I can delete my account. | 2 Med | Done
HOME PAGE | As a user, I want to access the Home Page so that I can display trending auctions. | 1 High | Done
AUCTIONS | As a user, I want to search for an auction so that I can display it. | 1 High | Done
| As a user, I want to select an auction from the trending ones so that I can display it. | 3 Med | Done
| As a registered user, I want to make an offer for an auction so that I can participate to it. | 1 High | Done
| As a user, I want to check the current leading offer of an auction so that I can decide if surpass it. | 1 High | Done
| As a registered user, I want to check the result an auction in which I offered so that I can know who won. | 1 High | Done
MY AUCTIONS | As a registered user, I want to create a new auction so that I can sell an object. | 1 High | Done
| As a registered user, I want to access the My Auction Page so that I can display the auctions I created. | 2 High | Done
| As a registered user, I want to access the My Offer Page so that I can display the auctions in which I offered. | 1 High | Done
Note on A1: Product Owner: Write the name of the story, drag rows according to priorities
Note on B1: Product Owner: Write a detailed description of the story. Be specific about high priority features Make new lines in the same cell with [alt+enter]
Note on D1: Product Owner: Select current status