## Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Definition |  | 21 | 23 | -2 | 1 |  |  |  | 109.5%
1.1 | Initial Discussion for Ideas | Everyone | 4 | 4 | 0 | 1 | 2023-11-28 | 2023-11-29 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T; WEEK 8 F
1.1.1 | Research of Information | Everyone | 5 | 5 | 0 | 1 | 2023-12-02 | 2023-12-03 | 2 | 100% | bar: WEEK 1 W to WEEK 1 F; WEEK 8 F
1.2 | Project Planning | Everyone | 8 | 10 | -2 | 1 | 2023-12-04 | 2023-12-07 | 4 | 125% | bar: WEEK 1 W to WEEK 2 R; WEEK 8 F
1.4 | Architecture Modeling | Everyone | 2 | 2 | 0 | 1 | 2023-12-11 | 2023-12-11 | 1 | 100% | bar: WEEK 2 R; WEEK 8 F
1.5 | Sent Project Proposal | Everyone | 2 | 2 | 0 | 1 | 2023-12-12 | 2023-12-12 | 1 | 100% | bar: WEEK 2 F; WEEK 8 F
2 | Project Setup |  | 20 | 20 | 0 | 2 |  |  |  | 100%
2.1 | User Stories | Everyone | 4 | 4 | 0 | 2 | 2022-07-18 | 2022-07-20 | 3 | 100% | bar: WEEK 3 M to WEEK 3 T; WEEK 8 F
2.2 | Wireframes | Everyone | 6 | 6 | 0 | 2 | 2022-07-20 | 2022-07-22 | 3 | 100% | bar: WEEK 3 W to WEEK 3 F; WEEK 8 F
2.3 | Function Points & COCOMO Estimation | Everyone | 4 | 4 | 0 | 2 | 2022-07-25 | 2022-07-25 | 1 | 100% | bar: WEEK 4 M to WEEK 4 T; WEEK 8 F
2,4 | Product Backlog | Everyone | 4 | 4 | 0 | 2 | 2022-07-27 | 2022-07-28 | 2 | 100% | bar: WEEK 4 W to WEEK 4 R; WEEK 8 F
2,5 | Documentation | Everyone | 2 | 2 | 0 | 2 | 2022-07-29 | 2022-07-29 | 1 | 100% | bar: WEEK 4 F; WEEK 8 F
3 | Back-End Implementation |  | 56 | 65 | -9 | 3 |  |  |  | 116.1%
3.1 | First version of the User Management Microservice | Casciani | 4 | 6 | -2 | 3 | 2022-07-28 | 2022-08-07 | 11 | 150% | bar: WEEK 5 M to WEEK 5 T; WEEK 5 R; WEEK 8 F
3,1,1 | DB for User Management Microservice | Casciani | 1 | 1 | 0 | 3 | 2022-07-29 | 2022-08-07 | 10 | 100% | bar: WEEK 5 M; WEEK 8 F
3,1,2 | User Management Functionalities | Casciani | 8 | 8 | 0 | 3 | 2022-07-29 | 2022-08-07 | 10 | 100% | bar: WEEK 5 M to WEEK 5 T; WEEK 8 F
3,2 | First version of the Notification Microservice | Casciani | 4 | 4 | 0 | 3 | 2022-08-04 | 2022-08-07 | 4 | 100% | bar: WEEK 5 W to WEEK 5 F; WEEK 8 F
3,2,1 | Subscription Model, Repository & Controller | Casciani | 6 | 6 | 0 | 3 | 2022-08-04 | 2022-08-07 | 4 | 100% | bar: WEEK 5 W; WEEK 8 F
3,1,5 | Notification Model, Repository & Controller | Casciani | 6 | 6 | 0 | 3 | 2022-08-04 | 2022-08-07 | 4 | 100% | bar: WEEK 5 W to WEEK 5 R; WEEK 8 F
3,3 | First Version of the Video Microservice | De Luca | 6 | 8 | -2 | 3 | 2022-08-08 | 2022-08-11 | 4 | 133.3% | bar: WEEK 6 M to WEEK 6 R; WEEK 8 F
3,3,1 | DB for videos | De Luca | 1 | 1 | 0 | 3 | 2022-08-08 | 2022-08-11 | 4 | 100% | bar: WEEK 6 M; WEEK 8 F
3,3,2 | Video, Comment and Like Models & Repositories | De Luca | 8 | 8 | 0 | 3 | 2022-08-08 | 2022-08-11 | 4 | 100% | bar: WEEK 6 M to WEEK 6 R; WEEK 8 F
3,3,3 | Controller for the Video Service | De Luca | 10 | 14 | -4 | 3 | 2022-08-09 | 2022-08-11 | 3 | 140% | bar: WEEK 6 T to WEEK 6 R; WEEK 8 F
3,4 | First Version of the Search Microservice | De Luca | 2 | 3 | -1 | 3 | 2022-08-12 | 2022-08-13 | 2 | 150% | bar: WEEK 6 F; WEEK 8 F
4 | Front-End & API Gateway |  | 104 | 118 | -14 | 4 |  |  |  | 113.5%
4.1 | Start Frontend Microservice (model-components-structure) | Casciani | 4 | 4 | 0 | 4 | 2022-08-10 | 2022-08-15 | 6 | 100% | bar: WEEK 6 W to WEEK 7 T; WEEK 8 F
4,1,2 | Defined URLs | Casciani | 2 | 2 | 0 | 4 | 2022-08-10 | 2022-08-15 | 6 | 100% | bar: WEEK 6 W to WEEK 7 T; WEEK 8 F
4,1,3 | Fix Video Management | Casciani | 3 | 3 | 0 | 4 | 2022-08-12 | 2022-08-15 | 4 | 100% | bar: WEEK 6 F to WEEK 7 M; WEEK 8 F
4,2,1 | ApiGateway Redirect | Casciani | 4 | 4 | 0 | 4 | 2022-08-14 | 2022-08-15 | 2 | 100% | bar: WEEK 7 M; WEEK 8 F
4,1,4 | Video Uploading from Frontend | Casciani | 4 | 8 | -4 | 4 | 2022-08-16 | 2022-08-17 | 2 | 200% | bar: WEEK 7 T to WEEK 7 W; WEEK 8 F
4,2,2 | Api Gateway Zuul | Casciani | 4 | 4 | 0 | 4 | 2022-08-17 | 2022-08-17 | 1 | 100% | bar: WEEK 7 W; WEEK 8 F
4,1,5 | Video Visualization | Casciani | 4 | 4 | 0 | 4 | 2022-08-18 | 2022-08-18 | 1 | 100% | bar: WEEK 7 R; WEEK 8 F
4,2,3 | S3 Support | Casciani | 4 | 4 | 0 | 4 | 2022-08-19 | 2022-08-19 | 1 | 100% | bar: WEEK 7 F; WEEK 8 F
4,2,4 | JWT Authentication users Backend | Casciani | 4 | 4 | 0 | 4 | 2022-08-20 | 2022-08-22 | 3 | 100% | bar: WEEK 7 F to WEEK 8 M; WEEK 8 F
4,2,5 | Api Gateway Filtering | Casciani | 4 | 7 | -3 | 4 | 2022-08-23 | 2022-08-24 | 2 | 175% | bar: WEEK 8 T to WEEK 8 W; WEEK 8 F
4,2,6 | RabbitMQ Communication video & notification MS | Casciani | 5 | 6 | -1 | 4 | 2022-08-25 | 2022-08-27 | 3 | 120% | bar: WEEK 8 R to WEEK 8 F
4,3 | Dockerfiles first version + Subscriptions Logic | Casciani | 4 | 4 | 0 | 4 | 2022-08-28 | 2022-08-28 | 1 | 100% | bar: WEEK 8 F
4,4 | Footer and Header | De Luca | 2 | 2 | 0 | 4 | 2022-08-22 | 2022-08-22 | 1 | 100% | bar: WEEK 8 M; WEEK 8 F
4,5 | Login and Sign Up Pages | De Luca | 4 | 3 | 1 | 4 | 2022-08-22 | 2022-08-22 | 1 | 75% | bar: WEEK 8 M; WEEK 8 F
4.6 | Home Page | De Luca | 6 | 7 | -1 | 4 | 2022-08-23 | 2022-08-23 | 1 | 116.7% | bar: WEEK 8 T; WEEK 8 F
4,7 | My Videos Page & Upload new Video frontend logic | De Luca | 10 | 12 | -2 | 4 | 2022-08-24 | 2022-08-25 | 2 | 120% | bar: WEEK 8 W to WEEK 8 F
4,8 | My profile Page | De Luca | 4 | 6 | -2 | 4 | 2022-08-25 | 2022-08-26 | 2 | 150% | bar: WEEK 8 R to WEEK 8 F
4,9 | Video Details Page | De Luca | 6 | 8 | -2 | 4 | 2022-08-26 | 2022-08-27 | 2 | 133.3% | bar: WEEK 8 F to WEEK 9 M
4,10 | Profile Page | De Luca | 6 | 6 | 0 | 4 | 2022-08-27 | 2022-08-27 | 1 | 100% | bar: WEEK 8 F to WEEK 9 M
4,11 | Search Page | De Luca | 4 | 4 | 0 | 4 | 2022-08-27 | 2022-08-28 | 2 | 100% | bar: WEEK 8 F to WEEK 9 M
4,12 | Edit-Video Page | De Luca | 4 | 4 | 0 | 4 | 2022-08-27 | 2022-08-28 | 2 | 100% | bar: WEEK 8 F to WEEK 9 M
4,13 | Subscription Page | De Luca | 6 | 8 | -2 | 4 | 2022-08-28 | 2022-08-29 | 2 | 133.3% | bar: WEEK 8 F to WEEK 9 M
4,14 | Notification Page | De Luca | 6 | 4 | 2 | 4 | 2022-08-29 | 2022-08-29 | 1 | 66.67% | bar: WEEK 8 F to WEEK 9 M
5 | Containerization and Frontend Fixes |  | 24 | 28 | -4 | 5 |  |  |  | 116.7%
5,1 | ElasticSearch Support | Casciani | 8 | 10 | -2 | 5 | 2022-08-29 | 2022-08-31 | 3 | 125% | bar: WEEK 8 F to WEEK 9 W
5,2 | Frontend fixes to home page and search page | De Luca | 6 | 6 | 0 | 5 | 2022-08-30 | 2022-09-01 | 3 | 100% | bar: WEEK 8 F; WEEK 9 T to WEEK 9 R
5,3 | Setup Docker | Casciani | 10 | 12 | -2 | 5 | 2022-08-30 | 2022-09-02 | 4 | 120% | bar: WEEK 8 F; WEEK 9 T to WEEK 9 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 225 | 254 | -29 | 60 | 3.75 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 |  | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 225 | 221.25 | 217.5 | 213.75 | 210 | 206.25 | 202.5 | 198.75 | 195 | 191.25 | 187.5 | 183.75 | 180 | 176.25 | 172.5 | 168.75 | 165 | 161.25 | 157.5 | 153.75 | 150 | 146.25 | 142.5 | 138.75 | 135 | 131.25 | 127.5 | 123.75 | 120 | 116.25 | 112.5 | 108.75 | 105 | 101.25 | 97.5 | 93.75 | 90 | 86.25 | 82.5 | 78.75 | 75 | 71.25 | 67.5 | 63.75 | 60 | 56.25 | 52.5 | 48.75 | 45 | 41 | 37 | 33 | 29 | 25 | 21 | 17 | 13 | 9 | 5 | 1
[10 empty] | ESTIMATE | 225 | 223 | 221 | 218 | 216 | 214 | 212 | 210 | 208 | 206 | 204 | 202 | 201 | 199 | 197 | 195 | 193 | 191 | 191 | 191 | 187 | 187 | 185 | 183 | 181 | 181 | 179 | 175 | 171 | 166 | 162 | 156 | 150 | 146 | 141 | 133 | 129 | 125 | 121 | 115 | 110 | 102 | 94 | 86 | 78 | 70 | 62 | 54 | 47 | 39 | 31 | 23 | 15 | 7 | -1 | -7 | -13 | -19 | -23 | -27 |  | 8018
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 4 | 0 | 2 | 2 | 2 | 0 | 2 | 4 | 4 | 5 | 4 | 6 | 6 | 4 | 5 | 8 | 4 | 4 | 4 | 6 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 4 | 2 |  | 257
[10 empty] | HRS REMAINING | 223 | 221 | 218 | 216 | 214 | 212 | 210 | 208 | 206 | 204 | 202 | 201 | 199 | 197 | 195 | 193 | 191 | 191 | 191 | 187 | 187 | 185 | 183 | 181 | 181 | 179 | 175 | 171 | 166 | 162 | 156 | 150 | 146 | 141 | 133 | 129 | 125 | 121 | 115 | 110 | 102 | 94 | 86 | 78 | 70 | 62 | 54 | 46 | 39 | 31 | 23 | 15 | 7 | -1 | -7 | -13 | -19 | -23 | -27 | -29 |  | 7763
[23 empty] | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 6
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Product Backlog
Story Name | Story Description | Priority | Status
SIGN-UP | As an unregistered user, I want to be able to register to the application so that I can access it | 1 High | Done
LOGIN | As a non-logged in registered user, I want to be able to login to the application so that I can use the application services | 1 High | Done
LOGOUT | As a registered user, I want to be able to logout from the application | 1 High | Done
MAIN | As a registered user, I want to be able to view the Main Page, so that I can visualize the latest videos | 1 High | Done
SUBSCRIPTIONS | As a registered user, I want to be able to subscribe to a user, so that I can quickly access his videos/profile | 4 Low | Done
| As a registered user, I want to be able to reach the Subscriptions Page, so that I can visualize the channels I subscribed to | 2 Med | Done
| As a registered user, I want to be able to view the Subscriptions Page, so that I can visualize the channels I subscribed to | 2 Med | Done
| As a registered user, I want to be able to be notified when one of my subscriptions uploads a new video, so that I can easily know about it | 4 Low | Done
MY VIDEO | As a registered user, I want to be able to upload a video, so that others can see it | 1 High | Done
| As a registered user, I want to be able to view the videos I have uploaded on the platform | 1 High | Done
| As a registered user, I want to be able to delete a video I previously uploaded so that others can't see it anymore | 1 High | Done
| As a registered user, I want to be able to edit a video's details uploaded on the application | 2 Med | Done
VIDEO | As a registered user, I want to be able to watch a Video uploaded on the application | 1 High | Done
| As a registered user, I want to be able to like/dislike/comment a video, so that I can interact with the content creator and his community | 3 Med | Done
SEARCH | As a registered user, I want to be able to search videos so that I can watch them | 1 High | Done
| As a registered user, I want to be able to search other users, so that I can watch his profile and videos | 2 Med | Done
PROFILE | As a registered user, I want to be able to reach my Profile page so that I can see my details | 2 Med | Done
| As a registered user, I want to be able to access another user's Profile page, so that I can see his details and his published videos | 3 Med | Done
| As a registered user, I want to be able to manage my profile | 2 Med | Done
| As a registered user, I want to be able to delete my account and all videos uploaded | 2 Med | Done
Note on A1: Product Owner: Write the name of the story, drag rows according to priorities
Note on B1: Product Owner: Write a detailed description of the story. Be specific about high priority features Make new lines in the same cell with [alt+enter]
Note on D1: Product Owner: Select current status